## Sheet1
The Backlog
Component | Assignee | Task Points | Success Scenario | Failure Scenario
As a Guest I should be able to sign up | Amr Nafie / Sandra Sherif | 10 | By using the Email and password, the user is able to sign up succcessfully and is redirected to his/her page | The Email could be invalid or already exists. The password also could be too short in which an alert message will come up to the user mentioning the error that went wrong in order for the user to correct it.
As a User/ admin I should be able to sign in | Amr Nafie / Sandra Sherif | 10 | By providing the correct Email and password the user should be able to sign in successfully and is redirected to his / her news feed | Upon failure to log in, an alert message will come up to the user identifying the error occurred whether it was a wrong email, password or both
As a user/ admin I should be able to sign out | Amr Nafie / Sandra Sherif | 9 | When the user clicks on the log out button he / she should be redirected to a page that shows a message saying that he signed out successfully | No Failure
As a user / admin I should be able to share posts on facebook, twitter and google plus | Christianne Iskandar / Omar Hady | 7 | Upon clicking on the sharing button below any post on the blog, a new tab should be opened for the permission to share that article or post on facebook, twitter or google plus | No Failure
As an admin I should be able to post articles | Marina ElDib | 10 | After posting the article, it should appear on the news feed and the profile of the admin | No Failure
As a User I should be able to comment on any post | Sarah Ameer | 8 | After viewing the post, the user should be able to comment and the comment should be viewed beneath the article commented on. | No failure
As an admin I should be able to destroy comments | Amr Nafie | 4 | The comment on the post should be deleted and disappear | No Failure
As a user I should be able to view latest posts | Haya Borham / Marina ElDib | 6 | - | -